## Project Status Dashboard
Project Budapest |  |  | Project Status Dashboard
| Project Status |  | Completed |  | 23% |  | Outstanding Issues
| Ongoing Activities: 5 |  |  | Project Plan |  | Click on the gantt chart to see it in detail
| Activity | % done
| System Build | 23%
| Interface Build | 32%
| Project Review | 64%
| Quality Standards Prep. | 12%
| Interface Testing | 15%
Top 5 Issues
Find test manager
Descope Risky Items
Start System Testing
Find more money
Demo to user group
| Burndown Chart |  |  |  |  | Project Timeline
Follow on Twitter
Visit the Blog
E-Mail Newsletter
RSS

## Data
Enter Project Status |  | Enter the Project Milestone Data Here |  |  | Top 5 Issues
Overall Project Status | Green | Date | Milestone if any | Height | Issue | Dummy
Overall Project Progress | 23% | 2009-05-01 | Project Kickoff | 1 | Find test manager | 0
|  | 2009-06-01 | First Prototype | 2 | Descope Risky Items | 0
Enter Activity Details |  | 2009-07-01 |  |  | Start System Testing | 0
|  | 2009-08-01 | Investor Presentation | 3 | Find more money | 0
|  | 2009-09-01 | Alpha Out | 4 | Demo to user group | 0
Ongoing Activities | 5 | 2009-10-01 |  |  |  | 0
|  | 2009-11-01 | Private Beta Out | 3 |  | 0
List of Activities |  | 2009-12-01 | Public Beta | 2 |  | 0
|  | 2010-01-01 |  |  |  | 0
Activity | Completion | 2010-02-01 | Roll out | 1 |  | 0
System Build | 23% | 2010-03-01 |  |  |  | 0
Interface Build | 32% | 2010-04-01 | Plan for future | 2 |  | 0
Project Review | 64%
Quality Standards Prep. | 12%
Interface Testing | 15%
Follow on Twitter
Visit the Blog
E-Mail Newsletter
RSS
Note on K3: Donot edit this

## Gantt Chart Template
Project Plan - Gantt Chart Template
|  | Planned |  | Actual |  | % | Show Gantt for | [5 empty] | Actual | [5 empty] | Show Status? |  |  |  |  | █ |  |  |  | What is current week? | [8 empty] | 3
# | List of Activties | Start | Dur | Start | Dur | Done | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
1 | Activity 1 | 1 | 5 | 1 | 2 | 0%
2 | Activity 2 | 1 | 5 | 1 | 6 | 58% | █ | █ | █ | █
3 | Activity 3 | 2 | 4 | 2 | 5 | 35% |  | █ | █
4 | Activity 4 | 4 | 8 | 2 | 6 | 10% |  | █
5 | Activity 5 | 4 | 1 | 3 | 8 | 0%
6 | Activity 6 | 4 | 3 | 4 | 6 | 0%
7 | Activity 7 | 5 | 4 | 4 | 3 | 0%
8 | Activity 8 | 5 | 2 | 4 | 5 | 0%
9 | Activity 9 | 5 | 2 | 4 | 6 | 0%
10 | Activity 10 | 6 | 5 | 6 | 7 | 0%
11 | Activity 11 | 6 | 1 | 7 | 8 | 0%
12 | Activity 12 | 9 | 3 | 8 | 3 | 0%
13 | Activity 13 | 9 | 6 | 8 | 6 | 0%
14 | Activity 14 | 9 | 3 | 9 | 1 | 0%
15 | Activity 15 | 9 | 4 | 9 | 4 | 0%
16 | Activity 16 | 10 | 5 | 10 | 2 | 0%
17 | Activity 17 | 11 | 2 | 10 | 5 | 0%
18 | Activity 18 | 12 | 6 | 11 | 7 | 0%
19 | Activity 19 | 12 | 1 | 11 | 5 | 0%
20 | Activity 20 | 14 | 5 | 11 | 6 | 0%
21 | Activity 21 | 14 | 8 | 11 | 1 | 0%
22 | Activity 22 | 14 | 7 | 11 | 3 | 0%
23 | Activity 23 | 15 | 4 | 12 | 8 | 0%
24 | Activity 24 | 15 | 5 | 14 | 3 | 0%
25 | Activity 25 | 15 | 8 | 14 | 5 | 0%
26 | Activity 26 | 16 | 8 | 15 | 1 | 28% | [14 empty] | █
27 | Activity 27 | 17 | 2 | 15 | 2 | 60% | [14 empty] | █ | █
28 | Activity 28 | 17 | 1 | 16 | 8 | 25% | [15 empty] | █ | █
29 | Activity 29 | 17 | 5 | 16 | 3 | 5% | [15 empty] | █
30 | Activity 30 | 18 | 1 | 16 | 3 | 16% | [15 empty] | █
31 | Activity 31 | 18 | 1 | 17 | 4 | 3% | [16 empty] | █
32 | Activity 32 | 19 | 6 | 18 | 7 | 41% | [17 empty] | █ | █ | █
33 | Activity 33 | 19 | 6 | 21 | 5 | 31% | [20 empty] | █ | █
34 | Activity 34 | 21 | 8 | 22 | 7 | 0%
35 | Activity 35 | 21 | 1 | 23 | 3 | 0%
36 | Activity 36 | 23 | 4 | 24 | 6 | 0%
37 | Activity 37 | 24 | 1 | 24 | 3 | 0%
38 | Activity 38 | 24 | 6 | 24 | 5 | 0%
39 | Activity 39 | 24 | 7 | 24 | 8 | 0%
40 | Activity 40 | 24 | 3 | 24 | 2 | 0%
4 | Sign up for e-mail updates and get more charting tutorials
4 | Add my RSS to your reading list
4 | Follow PHD on Twitter
4 | Visit Pointy Haired Dilbert Excel Tips Blog 4
Follow on Twitter
Visit the Blog
E-Mail Newsletter
RSS

## Burndown Chart
Burn down chart
Deliverable Burn Down
| Burned down |  | Balance |  | Daily Completed
Day | Planned | Actual | Planned | Actual
0 |  |  | 250 | 250 | #N/A
1 | 12 | 8 | 238 | 242 | 8
2 | 18 | 10 | 220 | 232 | 10
3 | 11 | 0 | 209 | 232 | 0
4 | 4 | 12 | 205 | 220 | 12
5 | 5 | 19 | 200 | 201 | 19
6 | 6 | 13 | 194 | 188 | 13
7 | 10 | 8 | 184 | 180 | 8
8 | 20 | 2 | 164 | 178 | 2
9 | 20 |  | 144 | #N/A | #N/A
10 | 18 | 2 | 126 | 176 | 2
11 | 6 |  | 120 | #N/A | #N/A
12 | 13 | 2 | 107 | 174 | 2
13 | 7 | 34 | 100 | 140 | 34
14 | 14 |  | 86 | #N/A | #N/A
15 | 12 |  | 74 | #N/A | #N/A
16 | 14 |  | 60 | #N/A | #N/A
17 | 12 |  | 48 | #N/A | #N/A
18 | 11 |  | 37 | #N/A | #N/A
19 | 19 |  | 18 | #N/A | #N/A
20 | 18 |  | 0 | #N/A | #N/A
Follow on Twitter
Visit the Blog
E-Mail Newsletter
RSS

## Issue Tracker
Issue Tracker Template
Date
# | Issue | Priority | Open | Close | Comments
1 | User name check fails | Low | 2009-07-12 | 2009-07-15
2 | Password field is not mandatory | Medium | 2009-07-12 | 2009-07-13
3 | Reset button doesn’t work | High | 2009-07-14 | 2009-07-19
4 | When window is maximized, the layout is compromised | Low | 2009-07-15 | 2009-07-16
5 | Password field takes more than 99 chars | Medium | 2009-07-15 | 2009-07-18
6 | User name allows SQL injection | Medium | 2009-07-15 | 2009-07-20
7 | Password allows SQL injection | Low | 2009-07-15 | 2009-07-22
8 | User name allows HTML Injection | High | 2009-07-16 | 2009-07-20
9 | Password allows HTML Injection | Low | 2009-07-16 | 2009-07-17
10 | Submit doesn’t work on enter | Medium | 2009-07-18 | 2009-07-25
11 | User name is not the default field on screen load | High | 2009-07-18 | 2009-07-24
12 | When hitting F5, the error message still remains | Low | 2009-07-18 | 2009-07-25
13 | Message is wrong | Medium | 2009-07-22 | 2009-07-24
14 | User name check fails | Medium | 2009-07-23 | 2009-07-28
15 | Password field is not mandatory | Low | 2009-07-23 | 2009-07-27
16 | Reset button doesn’t work | High | 2009-07-23 | 2009-07-30
17 | When window is maximized, the layout is compromised | Medium | 2009-07-23 | 2009-07-25
18 | Password field takes more than 99 chars | High | 2009-07-23 | 2009-07-28
19 | User name allows SQL injection | Low | 2009-07-24 | 2009-07-31
20 | Password allows SQL injection | Medium | 2009-07-24 | 2009-07-30
21 | User name allows HTML Injection | Medium | 2009-07-24 | 2009-07-30
22 | Password allows HTML Injection | Low | 2009-07-27 | 2009-08-02
23 | Submit doesn’t work on enter | High | 2009-07-28 | 2009-07-29
24 | User name is not the default field on screen load | Low | 2009-07-29 | 2009-08-02
25 | When hitting F5, the error message still remains | Medium | 2009-07-31 | 2009-08-07
26 | Message is wrong | High | 2009-08-01 | 2009-08-04
27 | User name check fails | Low | 2009-08-01 | 2009-08-05
28 | Password field is not mandatory | Medium | 2009-08-02 | 2009-08-09
29 | Reset button doesn’t work | Medium | 2009-08-04 | 2009-08-05
30 | When window is maximized, the layout is compromised | Medium | 2009-08-05 | 2009-08-12
31 | Password field takes more than 99 chars | High | 2009-08-05 | 2009-08-07
32 | User name allows SQL injection | Low | 2009-08-06 | 2009-08-09
33 | Password allows SQL injection | Medium | 2009-08-07 | 2009-08-09
34 | User name allows HTML Injection | Medium | 2009-08-07 | 2009-08-08
35 | Password allows HTML Injection | Low | 2009-08-10 | 2009-08-16
36 | Submit doesn’t work on enter | High | 2009-08-12 | 2009-08-19
37 | User name is not the default field on screen load | Low | 2009-08-14 | 2009-08-17
38 | When hitting F5, the error message still remains | Medium | 2009-08-15 | 2009-08-21
39 | Message is wrong | High | 2009-08-17 | 2009-08-24
40 | User name check fails | Low | 2009-08-18 | 2009-08-25
41 | Password field is not mandatory | Medium | 2009-08-21 | 2009-08-25
42 | Reset button doesn’t work | Medium | 2009-08-22 | 2009-08-27
43 | When window is maximized, the layout is compromised | High | 2009-08-22 | 2009-08-25
44 | Password field takes more than 99 chars | Low | 2009-08-22 | 2009-08-28
45 | User name allows SQL injection | Medium | 2009-08-22 | 2009-08-24
46 | Password allows SQL injection | High | 2009-08-24 | 2009-08-30
47 | User name allows HTML Injection | Low | 2009-08-24 | 2009-08-27
48 | Password allows HTML Injection | Medium | 2009-08-27
49 | Submit doesn’t work on enter | Medium | 2009-08-27
50 | User name is not the default field on screen load | Medium | 2009-08-29
51 | When hitting F5, the error message still remains | High | 2009-08-29
52 | Message is wrong | Low | 2009-08-29
53 | User name check fails | Medium | 2009-08-31
54 | Password field is not mandatory | Medium | 2009-09-01
55 | Reset button doesn’t work | Low | 2009-09-03
56 | When window is maximized, the layout is compromised | High | 2009-09-04
57 | Password field takes more than 99 chars | Low | 2009-09-05
58 | User name allows SQL injection | Medium | 2009-09-06
59 | Password allows SQL injection | High | 2009-09-07
60 | User name allows HTML Injection | Low | 2009-09-07
Follow on Twitter
Visit the Blog
E-Mail Newsletter
RSS

## Calculations
Open Issue Summary
High | 3
Medium | 6
Low | 4
Follow on Twitter
Visit the Blog
E-Mail Newsletter
RSS

## Legend
Types of Gantt | Gantt Chart Symbols
Planned | █
Actual | ○
↓
Follow on Twitter
Visit the Blog
E-Mail Newsletter
RSS